## Story and Task Matrix
Data below sourced from Trello project management tool
URL:https://trello.com/invite/b/qSLJuAbS/ATTI16aa859cfc485a05b57f79c2f0b9c27f351955EF/couchpotato-development
Percent of User Stories complete for this iteration: 100%
Percent of User Stories complete for entire project: 60%
Use Case or User Story | Status | List of Detailed Development Tasks | Estimate (hrs.) | Actual (hrs.) | Percent Complete | Notes
Product Filtering | In Progress | 1.Design UI for filters 2. Implement price range filter 3. Add category filters | 3h |  | 0%
Product Sorting | In Progress | 1. Design UI for sorting options. 2. Implement sorting by price. 3. Add sorting by popularity and rating. | 3h |  | 0%
View Order History | Blocked | 1. Design UI for order history page. 2. Fetch and display user's order history. | 3h | - | 0% | Unable to complete due to time constraints.
Manage Categories (Admin) | In Progress | 1. Design UI for category management. 2. Implement add, edit, delete category features. | 2h
Manage Brands (Admin) | Blocked | 1. Design UI for brand management. 2. Implement add, edit, delete brand features. | 3h | - | 0% | Unable to complete due to time constraints.
Manage Orders (Admin) | Blocked | 1. Design UI for order management. 2. Implement view, update order status features. 3. Generate sales and order reports. | 3h | - | 0% | Unable to complete due to time constraints.
Manage User Accounts (Admin) | Backlog | 1. Design UI for user account management. 2. Implement view, edit, delete user features. | 3h |  | 0%
Product Reviews/ Ratings | Blocked | 1. Design UI for product reviews. 2. Implement add, edit, delete review features. | 3h | - | 0% | Unable to complete due to time constraints.
Track Order Status | Blocked | 1. Design UI for order tracking. 2. Implement real-time order status updates. | 3h | - | 0% | Unable to complete due to time constraints.
Configure Application Settings (Admin) | Backlog | 1. Design UI for application settings. 2. Implement save, edit settings feature. | 3h |  | 0%
Checkout | In Progress | 1. Design UI for checkout page. 2. Implement shipping, billing info collection. 3. Integrate payment gateway. | 3h |  | 40%
User Registration | Testing | 1. Design UI for registration page. 2. Implement user data collection. 3. Implement email verification. | 2h | 1h | 80%
Product List | Testing | 1. Design UI for product listing. 2. Fetch and display products from database. | 2h | 1h | 80%
User Login | Testing | 1. Design UI for login page. 2. Implement authentication mechanism. | 2h | 1h | 80%
Add Products | Testing | 1. Design UI for adding product to a cart. 2. Implement add to cart functionality. | 2h | 1h | 80%
View Cart | Testing | 1. Design UI for cart page. 2. Implement cart item update functionality. | 2h | 1h | 80%
Remove Products | Testing | 1. Design UI for removing products from cart. 2. Implement remove from cart functionality. | 2h | 1h | 80%
Product Search | Testing | 1. Design UI for product search. 2. Implement search functionality. | 2h | 1h | 80%
Manage Products (Admin) | Testing | 1. Design UI for product management. 2. Implement, add, edit, delete product features. | 2h | 1h | 80%
Access From Multiple Devices | Testing | 1. Design responsive UI. 2. Test on multiple devices. | 2h | 1h | 80%
Product Recommendations | Blocked | 1. Design UI for product recommendations 2. Implement recommendation algorithm | 3h | - | 0% | Unable to complete due to time constraints.